## Sheet1
Requirements Matrix
|  | Facial Recognition Attendance System |  |  |  |  | Document Author: Brendon Stepanek
Req # Unique ID | Req. Description | Requested Approved | Scope Deliverables | User Story | Currently Assigned to | Test case | Current Status | Comments | Due Date
R1 | Define project objectives and scope | Approved | Project Charter | As a project manager, I want clearly defined objectives to guide the project. | Brendon | Veryify goals/objectives | Done | Initial task | 2025-01-31
R2 | Establish project timeline and milestones | Approved | Detailed project timeline | As a project manager, I want a clear timeline to track project progress. | Brendon | Ensure all milestones are defined | Done | Align with team deliverables | 2025-02-07
R3 | Assign team roles and responsibilities | Approved | Team roles and tasks assignments | As a project manager, I want clearly defined roles to distribute work effectively. | Brendon | Crosscheck with WBS | Done | Finalize after team input | 2025-02-08
R4 | Research and finalize a completed technology stack | Approved | Finalized Decisions on software/technology to be used | As a developer, I want to ensure the right tools and frameworks are chosen. | Brendon | Check stack feasibility | In Progress | With Joshua | 2025-02-15
R5 | Set up the Flask backend architecture | Approved | Functional backend architecture | As a developer, I want a well-structured backend to manage attendance records. | Brendon | Test API functionality | Not started | With Neel | 2025-02-26
R6 | Develop an attendance tracking API | Approved | Completed attendance tracking API | As a developer, I want an API to record attendance securely. | Brendon | Check API integration | Not started | Align with frontend team | 2025-03-06
R7 | Perform unit testing on backend APIs | Approved | Verified API functionality | As a tester, I want unit tests to ensure backend stability. | Brendon | Ensure all tests pass | Not started | Coverage >= 85% | 2025-03-15
R8 | Set up the React application | Approved | Functional frontend | As a developer, I want a working React frontend for user interaction. | Brendon | Check application functionality | Not started | Set up initial framework | 2025-03-17
R9 | Conduct unit testing on Backend APIs and database | Approved | Verify backend and database functionality | As a tester, I want tests to validate backend and database integrity. | Brendon | Check tests against requirements | Not started | Focus on major use cases | 2025-04-01
R10 | Deploy Flask backend on hosting service | Approved | Backend server hosting | As a teacher, I want the system available online for real-time access. | Brendon | Veryify API connectivity post-deployment | Not started | AWS/Heroku, service pending | 2025-04-09
R11 | Create developer documentation | Approved | Comprehensive developer documentation | As a developer, I need clear documentation for API usage and deployment. | Brendon | Ensure documentation is clear | Not started | Check with team | 2025-04-15
R12 | Create system architecture documentation | Approved | Comprehensive architectural documention of our system | As a developer, I want detailed diagrams for system structure. | Brendon | Compare against system design | Not started | Create draft of system overview | 2025-04-19
R13 | Monitor system performance and logs | Approved | Proper system monitoring setup | As an admin, I want tools to monitor system performance. | Brendon | Ensure logs provide important metrics/data | Not started | Note: AWS does provide some monitoring tools | 2025-04-23
Columns and Their Contents:
Requirement ID: Unique identifier for each requirement.
Requirement Description: Brief summary of each requirement.
Design Document: Reference to the design document that addresses the requirement.
Test Case: Reference to the test case that verifies the requirement.
User Manual: Reference to the user manual section that describes the requirement.
Additional Columns (Optional):
Priority: Priority level of each requirement (e.g., high, medium, low).
Risk: Risk level associated with each requirement (e.g., high, medium, low).
Assumptions: Assumptions made while defining each requirement.
Dependencies: Dependencies between requirements.
Status: Status of each requirement (e.g., in progress, completed, pending).